## Sheet1
visit date-13.07.2020
6300 Press Machine
| 1 | Scope of Work
|  | Panel Name on Field | PLC | GOT | Scope of work
|  | 1.Centralize Main PLC Panel | Mitsubishi Q02 CPU , QJ61BT11N | GT1000 | 1.add logic for Robot Program Selection. 2.remove Old robot logic from PLC program. 3.GOT screen Modifications 4.Alarm Programming and testing. 5.Io List Modifications. 6.Safty devices programming and testing. 7.Io testing 8.Final job trials and production support 9. 9.IO modifacation final drawings
|  | 2.RR panel | S7-300 | TP700 comfort | 1.PLC Program Modification 2.GOT screen Modifications 3.Alarm Programming and testing. 4.Io List Modifications. 5.Safty devices programming and testing. 6.Io testing 7.Final job trials and production support
|  | 3.Press Panel | S7-300 |  | 1.PLC Program Modification 2.GOT screen Modifications 3.Alarm Programming and testing. 4.Io List Modifications. 5.Safty devices programming and testing. 6.Io testing 7.final job trials and production support 8.IO modification drawings
|  | 4.IBH panel | S7-300 | TP177B DP 6STN | 1.PLC Program Modification 2.GOT screen Modifications 3.Alarm Programming and testing. 4.Io List Modifications. 5.Safty devices programming and testing. 6.Io testing 7.final job trials and production support
|  | 5.Gantry Panel in future |  |  | In future
|  | 6.Robot Panel | Fanuc |  | New Program Add and Teaching
|  | 7.Field wiring |  |  | 1.JB to all fild devices like solenoied,sensors as per drawings. 2.Panel to panel Hand shaking signals wiring. 3.sensor setting and fitting to bracket. 4terminations in all panels. 5.Panel to panel multicore wiring replacement if requires 6.io testing and wiring corrections
|  | Notes: | 1 | Centralize Main PLC Panel and Robot Panel on CC link Panel.
|  |  | 2 | Centralize main PLC panel and press panel H/w hand shking
|  |  | 3 | Centralize main PLC panel and IBH panel H/w hand shking
|  |  | 4 | Centralize main PLC panel and RR panel H/w hand shking
|  |  | 5 | Gantry Panel is requires in future
|  |  | 6 | Right now all field wires are in dismentelled stage.
|  | Scope Mahindra CIE | 1 | Mechanical work , Welding Work,scope in Mahidra CIE
|  |  | 2 | Sesors, solnoieds, JB's scope in Mahindra CIE
|  |  | 3 | Any Field Devices, PLC and HMI material ,Switchgear Scope in Mahindra CIE
|  |  | 4 | Any Cables for Field wiring or for panel wiring in Mahindra CIE scope
|  |  | 5 | Sensor's Bracket and its Mounting or
|  |  | 6 | JB Mounting or jb Shifting and Panel Mounting or Panel Shifting in Mahindra CIE scope
|  |  | 7 | Cable tray and its mounting in Mahindra CIE scope
|  |  | 7 | Mahidra CIE will provide us Commented back up. But as per visit right now they have no commented back up.
|  |  | 8 | Mahindra CIE will provide all panel Io list
|  |  | 9 | Mahindra CIE will provide all panel Drawings for field wiring
|  |  | 10 | Robot Programming and teaching in Mahindra CIE scope
|  |  | 11 | Alarm list in Mahindra CIE scope
|  |  | 12 | checking and testing of safty interlocks, Alarms, Auto cycle working, Manual Operations, Production trial, job trial support
|  |  | 13 | HMI programs modification requirements
|  |  | 14 | For field wiring ferrule, lugs and spiral ,conduit in Mahindra CIE scope
Scope Cubix Automation
|  |  | 1 | All Mitsubishi , Simens PLC and HMI programing in cubix scope
HMI programming as per requirement. Mahindra CIE will discuss and will tell what they requires
|  |  | 2 | Sensor Setting and fitting in Cubix Automation scope
|  |  | 3 | Field wiring in Cubix Automation Scope
|  |  | 4 | Alarm programming in Cubix Automation scope.
|  |  | 5 | Safty devices Programming in Cubix Automation scope
|  |  | 6 | Final trials
|  |  | 7 | Job Trials
|  |  | 8 | Production support